## Overview
Jira, Confluence & Xray Cloud Migration - Smoke Test Suite
Document Information
Project | Jira & Confluence On-Premises to Cloud Migration (SFDC Development / SFDC Operations, SFSUPPORTDE, Xray)
Release | Phase 1 - Test Environment Migration
Document Type | Migration Smoke Test Specification
Created Date | 2026-08-12
Last Updated | 2026-08-12
Status | Under Review
Author | QA Team
Reviewer | QA Lead / Migration Lead
Note on Field Mapping
This suite has no 'User Story' reference, so the 'Reference & Status' column carries each test's Priority (Critical/High/Medium/Low) instead. 'Test Detail' combines the source suite's Test Step and Test Action fields; 'Expected Outcome' reflects the Expected Result field.
Test Case Distribution by Category
Category | Test Count
1. Environment & Access | 5
2. Jira Project Validation | 9
3. Jira Issue Types | 13
4. Jira Configuration | 6
5. Jira Data Integrity | 5
6. Jira Links & Relationships | 5
7. Attachments (Jira) | 5
8. Search & Reporting (Jira) | 4
9. Scrum Boards | 4
10. Kanban Boards | 3
11. Sprint & Historical Data | 5
12. Xray | 9
13. Integrations | 3
14. Security & Permissions | 5
15. Confluence Space | 3
16. Confluence Pages | 5
17. Confluence Attachments | 4
18. Confluence Links | 4
19. Confluence Search | 3
20. Jira-Confluence Cross Validation | 3
21. Data Reconciliation | 6
22. Migration Exceptions | 5
23. Handover Readiness | 6
Total | 120
Priority Distribution
Priority | Test Count
Critical | 36
High | 51
Medium | 27
Low | 6
Total | 120
Test Execution Summary
Category | Total | Passed | Failed | Blocked | Pending
1. Environment & Access | 5 | - | - | - | 5
2. Jira Project Validation | 9 | - | - | - | 9
3. Jira Issue Types | 13 | - | - | - | 13
4. Jira Configuration | 6 | - | - | - | 6
5. Jira Data Integrity | 5 | - | - | - | 5
6. Jira Links & Relationships | 5 | - | - | - | 5
7. Attachments (Jira) | 5 | - | - | - | 5
8. Search & Reporting (Jira) | 4 | - | - | - | 4
9. Scrum Boards | 4 | - | - | - | 4
10. Kanban Boards | 3 | - | - | - | 3
11. Sprint & Historical Data | 5 | - | - | - | 5
12. Xray | 9 | - | - | - | 9
13. Integrations | 3 | - | - | - | 3
14. Security & Permissions | 5 | - | - | - | 5
15. Confluence Space | 3 | - | - | - | 3
16. Confluence Pages | 5 | - | - | - | 5
17. Confluence Attachments | 4 | - | - | - | 4
18. Confluence Links | 4 | - | - | - | 4
19. Confluence Search | 3 | - | - | - | 3
20. Jira-Confluence Cross Validation | 3 | - | - | - | 3
21. Data Reconciliation | 6 | - | - | - | 6
22. Migration Exceptions | 5 | - | - | - | 5
23. Handover Readiness | 6 | - | - | - | 6
Total | 120 | - | - | - | 120
Approval Sign-off
Role | Name | Signature | Date
QA Lead
Dev Lead
Product Owner
Release Manager
Revision History
Version | Date | Author | Changes
v1 | 2026-08-12 | QA Team | Initial Confluence-format conversion of the 120-test Jira/Confluence/Xray Cloud Migration smoke test suite.

## Coverage Matrix
Category | Test Case IDs | Coverage Status
1. Environment & Access | ENV-001, ENV-002, ENV-003, ENV-004, ENV-005 | ✅ Covered
2. Jira Project Validation | JIRA-001, JIRA-002, JIRA-003, DEV-001, DEV-002, DEV-003, OPS-001, OPS-002, OPS-003 | ✅ Covered
3. Jira Issue Types | JIRA-004, JIRA-005, JIRA-006, JIRA-007, JIRA-008, JIRA-009, JIRA-010, JIRA-011, JIRA-012, JIRA-013, JIRA-014, JIRA-015, JIRA-016 | ✅ Covered
4. Jira Configuration | CFG-001, CFG-002, CFG-003, CFG-004, CFG-005, CFG-006 | ✅ Covered
5. Jira Data Integrity | DATA-001, DATA-002, DATA-003, DATA-004, DATA-005 | ✅ Covered
6. Jira Links & Relationships | LINK-001, LINK-002, LINK-003, LINK-004, LINK-005 | ✅ Covered
7. Attachments (Jira) | ATT-001, ATT-002, ATT-003, ATT-004, ATT-005 | ✅ Covered
8. Search & Reporting (Jira) | SEARCH-001, SEARCH-002, SEARCH-003, SEARCH-004 | ✅ Covered
9. Scrum Boards | BOARD-001, BOARD-002, BOARD-003, BOARD-004 | ✅ Covered
10. Kanban Boards | BOARD-005, BOARD-006, BOARD-007 | ✅ Covered
11. Sprint & Historical Data | SPRINT-001, SPRINT-002, SPRINT-003, SPRINT-004, SPRINT-005 | ✅ Covered
12. Xray | XRAY-001, XRAY-002, XRAY-003, XRAY-004, XRAY-005, XRAY-006, XRAY-007, XRAY-008, XRAY-009 | ✅ Covered
13. Integrations | INT-001, INT-002, INT-003 | ✅ Covered
14. Security & Permissions | SEC-001, SEC-002, SEC-003, SEC-004, SEC-005 | ✅ Covered
15. Confluence Space | CONF-001, CONF-002, CONF-003 | ✅ Covered
16. Confluence Pages | CONF-004, CONF-005, CONF-006, CONF-007, CONF-008 | ✅ Covered
17. Confluence Attachments | CONF-009, CONF-010, CONF-011, CONF-012 | ✅ Covered
18. Confluence Links | LINK-006, LINK-007, LINK-008, LINK-009 | ✅ Covered
19. Confluence Search | SEARCH-005, SEARCH-006, SEARCH-007 | ✅ Covered
20. Jira-Confluence Cross Validation | LINK-010, LINK-011, LINK-012 | ✅ Covered
21. Data Reconciliation | DATA-006, DATA-007, DATA-008, DATA-009, DATA-010, DATA-011 | ✅ Covered
22. Migration Exceptions | EXC-001, EXC-002, EXC-003, EXC-004, EXC-005 | ✅ Covered
23. Handover Readiness | HAND-001, HAND-002, HAND-003, HAND-004, HAND-005, HAND-006 | ✅ Covered

## 01 Environment & Access
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
ENV-001 | Verify Jira Cloud URL and login | • Test Environment migration is complete • tester has a migrated Jira Cloud user account and the Cloud site URL | • Open the migrated Jira Cloud URL in a supported browser. • Enter the credentials of a migrated user (or authenticate via SSO if configured). • Observe the landing page after successful authentication. • Confirm the URL resolves to the correct Jira Cloud tenant (not the old On-Premises URL). • Confirm login succeeds without certificate, redirect, or authentication errors. • Confirm the user lands on the Jira Cloud dashboard/home screen. | • The Jira Cloud URL loads without error and displays the correct Cloud tenant. • The migrated user authenticates successfully and reaches the Jira home/dashboard screen without being redirected to the legacy On-Premises URL. | Critical | Pending
ENV-002 | Verify Confluence Cloud URL and login | • Test Environment migration is complete • tester has a migrated Confluence Cloud user account and the Cloud site URL | • Open the migrated Confluence Cloud URL in a supported browser. • Enter the credentials of a migrated user (or authenticate via SSO if configured). • Observe the landing page after successful authentication. • Confirm the URL resolves to the correct Confluence Cloud tenant. • Confirm login succeeds without certificate, redirect, or authentication errors. • Confirm the user lands on the Confluence Cloud home screen. | • The Confluence Cloud URL loads without error and displays the correct Cloud tenant. • The migrated user authenticates successfully and reaches the Confluence home screen without errors. | Critical | Pending
ENV-003 | Verify SSO/authentication for migrated users | • SSO/authentication has been configured for the Cloud tenant • at least one migrated user account is available for testing | • Navigate to the Jira Cloud login page and initiate SSO login (or standard login if SSO is not in scope). • Complete authentication using a migrated user identity. • Repeat steps 1-2 for the Confluence Cloud login page. • Verify the user is redirected to the correct identity provider (if SSO is used). • Verify the same migrated identity works for both Jira Cloud and Confluence Cloud. • Verify no duplicate/orphaned account prompts appear. | • The migrated user authenticates successfully on both Jira Cloud and Confluence Cloud using a single identity. • No authentication errors, account-linking prompts, or duplicate-account warnings occur. | Critical | Pending
ENV-004 | Verify project and space level access for authorized users | • A test user known to have had access to SFDC Development, SFDC Operations and the SFSUPPORTDE space in the source environment is available | • Log in to Jira Cloud as the test user. • Navigate to the SFDC Development and SFDC Operations projects. • Log in to Confluence Cloud as the same test user. • Navigate to the SFSUPPORTDE space. • Confirm the user can open both Jira projects without an authorization error. • Confirm the user can open the SFSUPPORTDE space without an authorization error. • Compare the resulting access level against the corresponding On-Premises/source access (<SOURCE_USER> access level). | • The test user can access SFDC Development, SFDC Operations, and SFSUPPORTDE without permission errors. • The user's access level in Cloud matches the access level recorded for <SOURCE_USER> in the source environment. | Critical | Pending
ENV-005 | Verify basic navigation and browser compatibility | • Test Environment migration is complete • tester has access to the supported browser(s) used by the organization | • Log in to Jira Cloud and navigate through the top navigation bar, project sidebar, and issue navigator. • Log in to Confluence Cloud and navigate through the space sidebar, page tree, and top navigation bar. • Repeat on any additional officially supported browser. • Confirm all primary navigation menus render and respond to clicks. • Confirm no layout/rendering errors are present. • Confirm no JavaScript console errors block core navigation (where tester tooling allows). | • All primary Jira Cloud and Confluence Cloud navigation elements load and function correctly in the supported browser(s). • No blocking rendering or navigation errors are observed. | Medium | Pending

## 02 Jira Project Validation
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
JIRA-001 | Verify both migrated Jira projects are listed | • Test Environment migration is completed • tester has valid Jira Cloud access | • Log in to Jira Cloud. • Navigate to Projects > View all projects. • Locate SFDC Development and SFDC Operations in the list. • Verify both project names appear exactly as in the source environment. • Verify both project keys are displayed alongside the project names. • Verify both projects can be opened from the directory. | • SFDC Development and SFDC Operations are both listed in the Projects directory with the expected project names and keys. • Both projects open successfully when selected. | Critical | Pending
JIRA-002 | Verify issue creation works in migrated projects | • Tester has Create Issue permission in SFDC Development and SFDC Operations | • Open SFDC Development and select Create issue. • Select an available issue type (e.g. Task) and populate the mandatory fields. • Submit the issue and note the generated issue key. • Repeat steps 1-3 for SFDC Operations. • Verify the issue type list matches the expected migrated issue type scheme. • Verify mandatory fields are enforced as expected. • Verify the new issue is created and opens successfully in each project. | • A new issue can be created successfully in both SFDC Development and SFDC Operations without configuration errors. • Each new issue receives a valid issue key using the project's expected key prefix. | High | Pending
JIRA-003 | Verify issue editing, viewing, and transitions work in migrated projects | • A known migrated issue key is available in each project • tester has Edit/Transition permissions | • Open <SOURCE_ISSUE_KEY> in SFDC Development. • Edit a non-critical field (e.g. add a label) and save. • Perform an available workflow transition and confirm the new status. • Repeat steps 1-3 using an equivalent issue in SFDC Operations. • Verify the edit is saved without error. • Verify the workflow transition options match the expected migrated workflow. • Verify the issue status updates correctly after the transition. | • Issues in both projects can be viewed, edited, and transitioned without errors. • The workflow transitions offered match the expected source workflow for the issue type. | High | Pending
DEV-001 | Verify SFDC Development project identity and configuration | • Test Environment migration is completed • tester has access to SFDC Development | • Navigate to the SFDC Development project. • Open Project settings > Details. • Compare the Project key, Project name, Project type, and Project lead against the source environment. • Compare the Cloud value against the corresponding On-Premises/source value for project key, name, type, and lead. • Verify the project category (if used) is preserved. | • SFDC Development displays the same project key, name, project type, and lead as the source environment. • No configuration discrepancies are found when compared to <SOURCE_COUNT>/source configuration records. | Critical | Pending
DEV-002 | Verify SFDC Development project roles and permissions | • Tester has Project Administrator access to SFDC Development | • Open SFDC Development > Project settings > People. • Review the members assigned to each project role. • Open Project settings > Permissions and review the associated permission scheme. • Compare project role membership against the source environment's role assignments (<SOURCE_USER> mappings). • Verify the permission scheme name and key permission grants match the source configuration. | • Project roles in SFDC Development contain the expected migrated members. • The permission scheme applied matches the source environment's permission scheme and grants. | High | Pending
DEV-003 | Verify SFDC Development versions, components, and issue type scheme | • Tester has access to SFDC Development project settings | • Open Project settings > Versions and review the list of versions/releases. • Open Project settings > Components and review components and their leads. • Open Project settings > Issue types and review the associated issue type scheme. • Compare the versions list, release/status flags, and dates against the source environment. • Compare each component name and component lead against the source environment. • Compare the issue types available to the project against the expected 13 issue types in scope. | • Versions, components (with correct leads), and the issue type scheme in SFDC Development match the source environment. • All expected issue types remain associated with the project. | High | Pending
OPS-001 | Verify SFDC Operations project identity and configuration | • Test Environment migration is completed • tester has access to SFDC Operations | • Navigate to the SFDC Operations project. • Open Project settings > Details. • Compare the Project key, Project name, Project type, and Project lead against the source environment. • Compare the Cloud value against the corresponding On-Premises/source value for project key, name, type, and lead. • Verify the project category (if used) is preserved. | • SFDC Operations displays the same project key, name, project type, and lead as the source environment. • No configuration discrepancies are found when compared to the source configuration records. | Critical | Pending
OPS-002 | Verify SFDC Operations project roles and permissions | • Tester has Project Administrator access to SFDC Operations | • Open SFDC Operations > Project settings > People. • Review the members assigned to each project role. • Open Project settings > Permissions and review the associated permission scheme. • Compare project role membership against the source environment's role assignments (<SOURCE_USER> mappings). • Verify the permission scheme name and key permission grants match the source configuration. | • Project roles in SFDC Operations contain the expected migrated members. • The permission scheme applied matches the source environment's permission scheme and grants. | High | Pending
OPS-003 | Verify SFDC Operations versions, components, and issue type scheme | • Tester has access to SFDC Operations project settings | • Open Project settings > Versions and review the list of versions/releases. • Open Project settings > Components and review components and their leads. • Open Project settings > Issue types and review the associated issue type scheme. • Compare the versions list, release/status flags, and dates against the source environment. • Compare each component name and component lead against the source environment. • Compare the issue types available to the project against the expected issue types in scope. | • Versions, components (with correct leads), and the issue type scheme in SFDC Operations match the source environment. • All expected issue types remain associated with the project. | High | Pending

## 03 Jira Issue Types
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
JIRA-004 | Verify migrated Bug issue type retains core data | • A known source Bug issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Bug using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Bug and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Bug issue is retrievable by its expected issue key and displays Bug as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | Critical | Pending
JIRA-005 | Verify migrated Epic issue type retains core data | • A known source Epic issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Epic using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Epic and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Epic issue is retrievable by its expected issue key and displays Epic as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | Critical | Pending
JIRA-006 | Verify migrated Feature issue type retains core data | • A known source Feature issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Feature using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Feature and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Feature issue is retrievable by its expected issue key and displays Feature as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending
JIRA-007 | Verify migrated Pre-condition issue type retains core data | • A known source Pre-condition issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Pre-condition using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Pre-condition and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Pre-condition issue is retrievable by its expected issue key and displays Pre-condition as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending
JIRA-008 | Verify migrated Spike issue type retains core data | • A known source Spike issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Spike using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Spike and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Spike issue is retrievable by its expected issue key and displays Spike as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | Medium | Pending
JIRA-009 | Verify migrated Sub-test Execution issue type retains core data | • A known source Sub-test Execution issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Sub-test Execution using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Sub-test Execution and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Sub-test Execution issue is retrievable by its expected issue key and displays Sub-test Execution as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending
JIRA-010 | Verify migrated Sub-task issue type retains core data | • A known source Sub-task issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Sub-task using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Sub-task and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Sub-task issue is retrievable by its expected issue key and displays Sub-task as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending
JIRA-011 | Verify migrated Task issue type retains core data | • A known source Task issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Task using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Task and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Task issue is retrievable by its expected issue key and displays Task as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending
JIRA-012 | Verify migrated Test issue type retains core data | • A known source Test issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Test using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Test and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Test issue is retrievable by its expected issue key and displays Test as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | Critical | Pending
JIRA-013 | Verify migrated Test Execution issue type retains core data | • A known source Test Execution issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Test Execution using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Test Execution and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Test Execution issue is retrievable by its expected issue key and displays Test Execution as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | Critical | Pending
JIRA-014 | Verify migrated Test Plan issue type retains core data | • A known source Test Plan issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Test Plan using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Test Plan and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Test Plan issue is retrievable by its expected issue key and displays Test Plan as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending
JIRA-015 | Verify migrated Test Set issue type retains core data | • A known source Test Set issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated Test Set using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as Test Set and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated Test Set issue is retrievable by its expected issue key and displays Test Set as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending
JIRA-016 | Verify migrated User Story issue type retains core data | • A known source User Story issue key (<SOURCE_ISSUE_KEY>) is available • tester has access to the migrated project | • Search for the migrated User Story using its issue key <SOURCE_ISSUE_KEY>. • Open the issue and confirm the Issue Type field shows the correct type. • Review Summary, Description, Status, Priority, Reporter, Assignee, Components, Versions, Labels and custom fields. • Review comments, attachments, issue links, parent/child relationships (where applicable), and issue history. • Verify the issue type is displayed as User Story and matches the source issue type. • Compare each field value against the corresponding source issue. • Verify comments, attachments, links, and history are present and complete. | • The migrated User Story issue is retrievable by its expected issue key and displays User Story as its issue type. • All core field values, comments, attachments, links, and history match the corresponding source issue with no data loss. | High | Pending

## 04 Jira Configuration
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
CFG-001 | Verify workflow statuses and transitions | • Tester has access to a migrated issue in each key workflow (e.g. Bug, Task, Test Execution) | • Open a migrated issue and review the available status. • Attempt each available workflow transition in turn (in a non-production-impacting manner). • Where configured, attempt a transition that should be blocked by a condition/validator. • Compare the list of statuses and available transitions against the source workflow diagram/configuration. • Verify transitions restricted by conditions/validators behave the same as in the source environment. • Verify post-function side effects (e.g. auto-assign, field updates) occur as expected. | • The workflow statuses and transitions available on the migrated issue match the source workflow definition. • Conditions, validators, and post-functions behave consistently with the source environment. | High | Pending
CFG-002 | Verify screens and screen schemes | • Tester has access to create and edit issues of multiple issue types in both projects | • Open the Create Issue screen for a given issue type and review the fields presented. • Open an existing issue and review the fields on the View/Edit screen. • Repeat for at least 3 different issue types (e.g. Bug, Test, User Story). • Compare the fields shown on each screen against the expected screen scheme configuration from the source environment. • Verify field order and required/optional indicators match expectations. | • Create, Edit, and View screens display the expected fields for each issue type, consistent with the source screen scheme configuration. • No fields are unexpectedly missing or duplicated. | Medium | Pending
CFG-003 | Verify custom fields and field configurations | • A list of key custom fields in scope is available • tester has access to a representative migrated issue using those fields | • Open a migrated issue that uses several custom fields. • Review each custom field's label, type (e.g. select list, text, date), and populated value. • Open the field configuration (where accessible) and confirm required/optional and field description settings. • Compare each custom field's label, type, options, and value against the source issue. • Verify field configuration behavior (required/hidden/optional) matches the source environment. | • All reviewed custom fields display the correct label, type, options, and value consistent with the source issue. • Field configuration behavior matches the source environment. | High | Pending
CFG-004 | Verify priorities and resolutions | • Tester has access to Jira Cloud administration or can view priority/resolution values on migrated issues | • Open a migrated issue and review the Priority field options. • Open a migrated closed issue and review the Resolution field value. • Where admin access is available, review the full Priorities and Resolutions configuration lists. • Compare the list of available priorities against the source environment's priority scheme. • Compare the list of available resolutions against the source environment's resolution scheme. | • All priorities and resolutions from the source environment are present and selectable/displayed correctly in Jira Cloud. • No priority or resolution values are missing or renamed unexpectedly. | Medium | Pending
CFG-005 | Verify notification schemes and permission schemes | • Tester has Project Administrator access and can trigger a test notification event (e.g. issue creation/comment) | • Open Project settings > Notifications for SFDC Development and SFDC Operations and review the configured events/recipients. • Create or comment on a test issue to trigger a notification event. • Confirm the expected recipient(s) receive the notification (or verify the configuration matches expectations if live email testing is out of scope). • Compare the notification scheme configuration against the source environment. • Verify the permission scheme referenced by Project settings > Permissions matches the source scheme name and grants. | • Notification scheme events and recipients match the source configuration, and a test event generates the expected notification. • The permission scheme in use matches the source environment. | Medium | Pending
CFG-006 | Verify issue security schemes and project settings | • A migrated issue with issue-level security applied is available • tester has Project Administrator access | • Open a migrated issue configured with an Issue Security Level. • Confirm the security level shown and the users/roles able to view it. • Open Project settings > general settings and review remaining configuration values. • Compare the issue security level and its associated visibility rules against the source environment. • Compare general project settings values against the source configuration. | • The issue security scheme is preserved and restricts visibility consistent with the source environment. • General project settings match the expected source configuration. | High | Pending

## 05 Jira Data Integrity
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
DATA-001 | Verify representative recent and historical issues migrated correctly | • A recent source issue key and an old source issue key are available for each project | • Open a recently created issue (<SOURCE_ISSUE_KEY>) in SFDC Development. • Open an old/historical issue (<SOURCE_ISSUE_KEY>) in SFDC Development. • Repeat steps 1-2 for SFDC Operations. • Compare all core fields of the recent issue against the source record. • Compare all core fields of the old/historical issue against the source record. | • Both recent and historical issues in each project display complete and accurate data matching the source environment. • No data degradation is observed for older records. | Critical | Pending
DATA-002 | Verify open and closed issue status preservation | • A known open issue key and a known closed issue key are available in each project | • Open a known open issue and confirm its Status field. • Open a known closed/resolved issue and confirm its Status and Resolution fields. • Compare the Status of the open issue against the source environment. • Compare the Status and Resolution of the closed issue against the source environment. | • The open issue displays the same status as in the source environment. • The closed issue displays the same status and resolution as in the source environment. | High | Pending
DATA-003 | Verify high-priority issue data integrity | • A list of known high-priority source issue keys is available | • Open each high-priority issue (<SOURCE_ISSUE_KEY>) in the migrated project. • Review Priority, Status, Assignee, Reporter, and any escalation-related custom fields. • Compare Priority and related field values against the source record for each issue. • Confirm no high-priority issue is missing from the migrated project. | • All sampled high-priority issues are present in Cloud with Priority and related fields matching the source environment. • No high-priority issue is found to be missing. | Critical | Pending
DATA-004 | Verify issues with comments, attachments, and multiple links preserved | • A known source issue key containing comments, attachments, and multiple links is available | • Open <SOURCE_ISSUE_KEY> and count the number of comments, attachments, and issue links. • Open each comment and confirm author, timestamp, and content. • Open each attachment and confirm it opens correctly. • Open each linked issue and confirm the link type and target. • Compare comment count, author, timestamp, and content against the source issue. • Compare attachment count and integrity against the source issue. • Compare link count, link type, and link target against the source issue. | • The migrated issue shows the same number of comments, attachments, and links as the source, with matching content, authorship, and timestamps. • All attachments open without corruption and all links resolve to the correct migrated targets. | High | Pending
DATA-005 | Verify issues with subtasks, Epic links, versions, and component associations preserved | • A known source issue key with subtasks and Epic/Version/Component associations is available | • Open <SOURCE_ISSUE_KEY> and review its subtasks (if any). • Review the Epic Link (or parent Epic) field. • Review the Fix Version(s), Affects Version(s), and Component(s) fields. • Compare subtask list and status against the source issue. • Compare the Epic association against the source issue. • Compare Version and Component assignments against the source issue. | • Subtasks, Epic association, Versions, and Components on the migrated issue match the source issue exactly. • No subtask, Epic link, version, or component assignment is missing. | High | Pending

## 06 Jira Links & Relationships
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
LINK-001 | Verify 'Blocks/is blocked by' issue links | • A known pair of source issues with a Blocks/is blocked by relationship is available | • Open the blocking issue (<SOURCE_ISSUE_KEY>) and locate the Blocks link in the Linked Issues section. • Click through to the blocked issue. • Open the blocked issue and confirm the reciprocal 'is blocked by' link back to the first issue. • Verify the link type label matches 'blocks'/'is blocked by' as in the source. • Verify clicking the link navigates to the correct migrated Cloud issue (not a broken/legacy URL). | • The Blocks/is blocked by relationship is present on both issues and navigates correctly between the migrated Cloud issues. • The link type and direction match the source environment. | High | Pending
LINK-002 | Verify 'Relates to' and 'Duplicates/is duplicated by' issue links | • Known source issue pairs with 'Relates to' and 'Duplicates' relationships are available | • Open an issue (<SOURCE_ISSUE_KEY>) with a 'Relates to' link and confirm the linked issue. • Open an issue (<SOURCE_ISSUE_KEY>) with a 'Duplicates'/'is duplicated by' link and confirm the linked issue. • Verify the link type and target match the source environment for both relationship types. • Verify both links navigate to the correct migrated Cloud issue. | • 'Relates to' and 'Duplicates/is duplicated by' links are present with the correct type and target, and navigate correctly to migrated Cloud issues. • No relationship data is lost. | Medium | Pending
LINK-003 | Verify parent/child, Epic/child-issue, and subtask/parent relationships | • A known Epic with child issues and a known parent issue with subtasks are available | • Open the Epic (<SOURCE_ISSUE_KEY>) and review its list of child issues. • Open one child issue and confirm the Epic Link field points back to the correct Epic. • Open a parent issue with subtasks and confirm each subtask is listed and correctly linked. • Compare the child issue list on the Epic against the source environment. • Compare the subtask list and status against the source environment. | • The Epic displays the correct, complete list of child issues, and each child correctly references its Epic. • Subtasks remain correctly associated with their parent issue. | High | Pending
LINK-004 | Verify remote links and cross-project links between SFDC Development and SFDC Operations | • A known issue with a remote link and a known cross-project link between the two projects are available | • Open an issue (<SOURCE_ISSUE_KEY>) containing a remote link and click through to the destination. • Open an issue in SFDC Development that is linked to an issue in SFDC Operations and click through to it. • Verify the remote link destination is correct and reachable (or documented as an expected exception if the destination system is out of migration scope). • Verify the cross-project link opens the correct migrated Cloud issue in SFDC Operations. | • The remote link resolves to the expected destination (or is documented as an expected exception). • The cross-project link successfully opens the corresponding migrated issue in the target project. | Medium | Pending
LINK-005 | Verify Xray test-to-requirement relationships (issue link level) | • A known requirement issue (e.g. User Story) linked to one or more Test issues via Xray is available | • Open the requirement issue (<SOURCE_ISSUE_KEY>) and locate the 'Tests'/'is tested by' link section. • Click through to each linked Test issue. • Confirm the Test issue's reciprocal link back to the requirement. • Verify the number and identity of linked Test issues matches the source environment. • Verify the reciprocal link is present and correctly typed on the Test issue. | • The requirement issue shows the correct set of linked Test issues, and each Test issue reciprocally links back to the requirement. • No test-to-requirement relationship is lost. | Critical | Pending

## 07 Attachments (Jira)
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
ATT-001 | Verify attachment presence and count on a representative issue | • A known source issue key with multiple attachments (<SOURCE_ATTACHMENT_NAME> list) is available | • Open <SOURCE_ISSUE_KEY> and open the Attachments panel. • Count the number of attachments and list their filenames. • Compare the attachment count against the source issue. • Compare each attachment filename against the source issue's attachment list. | • The migrated issue displays the same number of attachments as the source issue, with matching filenames. • No attachment is missing or renamed. | High | Pending
ATT-002 | Verify attachments can be opened and downloaded without corruption | • A known source issue with at least one downloadable attachment is available | • Open <SOURCE_ISSUE_KEY> and select an attachment to preview (if supported) and to download. • Open the downloaded file locally. • Compare the file size/content against the equivalent source file where available. • Verify the file opens without a corruption or format error. • Verify the downloaded file size and content are consistent with <SOURCE_ATTACHMENT_NAME>. | • The attachment opens and downloads successfully, and the file content is intact and matches the source file. • No corruption, truncation, or format error is observed. | High | Pending
ATT-003 | Verify image attachments render correctly | • A known source issue with an image attachment is available | • Open <SOURCE_ISSUE_KEY> and locate an image attachment. • View the thumbnail preview. • Open the full-size image view. • Verify the thumbnail renders without a broken-image icon. • Verify the full-size image displays correctly with no distortion, truncation, or missing content. | • The image attachment renders correctly as both a thumbnail and in full view, matching the expected source image. • No broken image indicators are present. | Medium | Pending
ATT-004 | Verify document attachments open correctly | • A known source issue with a document attachment of a type actually present in the source environment is available | • Open <SOURCE_ISSUE_KEY> and locate the document attachment. • Open/download the document using the appropriate application. • Review the document content for completeness. • Verify the document opens without an application/format error. • Verify the document content matches the expected source content (page count, key sections, embedded objects). | • The document attachment opens correctly and its content is complete and unmodified compared to the source file. • No corruption or missing content is observed. | Medium | Pending
ATT-005 | Verify representative large attachments are accessible | • A known source issue containing a large attachment (<SOURCE_ATTACHMENT_NAME>) is available | • Open the issue containing the large attachment. • Attempt to preview (if supported) and download the attachment. • Confirm the download completes and the file opens correctly. • Verify the download completes without timeout or truncation. • Verify the file size matches the source file size. | • The large attachment downloads completely and opens without corruption, with a file size matching the source. • No timeout, truncation, or size mismatch is observed. | Medium | Pending

## 08 Search & Reporting (Jira)
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
SEARCH-001 | Verify basic issue search returns migrated issues | • A known migrated issue key and a known keyword from its summary are available | • Use the Jira Cloud quick search bar to search for <SOURCE_ISSUE_KEY>. • Use the quick search bar to search for a known keyword from the issue's summary. • Verify the issue key search returns the correct issue directly. • Verify the keyword search returns the expected issue in the result list. | • Searching by issue key returns the correct migrated issue. • Searching by keyword returns the expected issue among the results. | High | Pending
SEARCH-002 | Verify advanced JQL search across projects, issue types, and fields | • Tester has access to the Advanced issue search (JQL) screen | • Run a JQL query filtering by project = SFDC Development. • Run a JQL query filtering by issue type, status, assignee, priority, version, and component individually. • Run a JQL query filtering by a known custom field value. • Verify each JQL query returns results consistent with the expected filter criteria. • Verify known migrated issues appear in the results when they meet the filter criteria. | • All JQL queries return accurate, filtered results consistent with the criteria used, and known migrated issues are found as expected. • No JQL query errors occur due to missing/misconfigured fields. | High | Pending
SEARCH-003 | Verify saved filters and dashboard gadgets display migrated data | • A known saved filter name and a dashboard using that filter are available | • Open Issues > Saved filters and locate the known saved filter. • Run the saved filter and review the results. • Open the dashboard containing a gadget based on this filter and review the gadget output. • Verify the saved filter's JQL and results match expectations from the source environment. • Verify the dashboard gadget renders results consistent with the underlying filter. | • The saved filter runs successfully and returns the expected migrated issues. • The dashboard gadget referencing the filter displays consistent, accurate data. | Medium | Pending
SEARCH-004 | Verify historical issue search across sprints and versions | • A known closed sprint name (<SOURCE_SPRINT_NAME>) and a known past version are available | • Run a JQL search filtering by the closed sprint name. • Run a JQL search filtering by a past/released version. • Verify the issues returned match the expected set of issues from the source environment for that sprint/version. • Verify no unexpected issues are missing from the historical result set. | • Historical searches by closed sprint and past version return the complete, correct set of migrated issues. • No historical data is found to be missing from search results. | Medium | Pending

## 09 Scrum Boards
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
BOARD-001 | Verify Scrum board availability, name, and filter | • A known Scrum board name is available for the in-scope project | • Navigate to the project's Boards section. • Open the Scrum board and confirm its name. • Open the board's configuration and review the board filter (saved JQL filter). • Compare the board name against the source environment. • Compare the board filter JQL against the source environment. | • The Scrum board is available with the expected name and its underlying filter matches the source configuration. • The board opens without errors. | High | Pending
BOARD-002 | Verify Scrum board columns and status mapping | • Tester has access to the migrated Scrum board configuration | • Open the Scrum board configuration > Columns. • Review each column name and the statuses mapped to it. • Compare the column names and status mappings against the source board configuration. | • Scrum board columns and status mappings match the source environment exactly. • No status is left unmapped or mapped to the wrong column. | Medium | Pending
BOARD-003 | Verify Scrum board quick filters and swimlanes | • Tester has access to the migrated Scrum board | • Open the Scrum board and review the available quick filters. • Apply each quick filter and confirm the board updates accordingly. • Review the swimlane configuration (e.g. by Epic, by Assignee, or custom JQL swimlanes). • Compare quick filter names/JQL against the source configuration. • Compare swimlane configuration against the source configuration. | • Quick filters and swimlanes match the source board configuration and function correctly when applied. • No quick filter or swimlane is missing. | Medium | Pending
BOARD-004 | Verify Scrum board backlog, active sprint, and future sprint visibility | • Tester has access to the migrated Scrum board with at least one active and one future sprint | • Open the Backlog view for the Scrum board. • Review the active sprint section and its issue list. • Review future sprint sections and the backlog (unscheduled) section. • Compare the active sprint's issue list against the source environment. • Compare future sprint contents and backlog issue order/ranking against the source environment. | • The Backlog view correctly displays the active sprint, future sprints, and backlog issues consistent with the source environment. • Issue ranking/order is preserved. | High | Pending

## 10 Kanban Boards
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
BOARD-005 | Verify Kanban board availability and filter | • A known Kanban board name is available for the in-scope project | • Navigate to the project's Boards section. • Open the Kanban board and confirm its name. • Review the board's underlying filter. • Compare the board name and filter JQL against the source environment. | • The Kanban board is available with the expected name and its filter matches the source configuration. • The board opens without errors. | Medium | Pending
BOARD-006 | Verify Kanban board columns, status mapping, and swimlanes | • Tester has access to the migrated Kanban board configuration | • Open the Kanban board configuration > Columns and review column/status mapping. • Review the swimlane configuration. • Review any configured quick filters. • Compare columns, status mapping, swimlanes, and quick filters against the source configuration. | • Kanban board columns, status mapping, swimlanes, and quick filters match the source environment. • No status is left unmapped. | Medium | Pending
BOARD-007 | Verify Kanban board ranking and historical data | • Tester has access to the migrated Kanban board with historical completed issues | • Open the Kanban board and review the current issue ranking/order in each column. • Review the 'Done'/completed issues history (if the board retains historical data). • Compare issue ranking/order against the expected source order. • Compare historical completed issue data against the source environment. | • Kanban issue ranking and historical completed issue data are preserved and consistent with the source environment. | Low | Pending

## 11 Sprint & Historical Data
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
SPRINT-001 | Verify sprint names, dates, and status preserved | • A known sprint name (<SOURCE_SPRINT_NAME>) is available for comparison | • Open the board's Backlog or Reports view and locate the sprint <SOURCE_SPRINT_NAME>. • Review the sprint's start date, end date, and status. • Compare the sprint name, dates, and status against the source environment. | • The sprint name, start/end dates, and status match the source environment exactly. | High | Pending
SPRINT-002 | Verify completed sprint history and issue membership | • A known closed sprint name (<SOURCE_SPRINT_NAME>) with a known issue list is available | • Open the Reports section for the board and select the closed sprint. • Review the list of issues that were completed, not completed, and added/removed during the sprint. • Compare the completed/incomplete/removed issue lists against the source environment's sprint report. | • The closed sprint's issue membership and completion outcome match the source environment. • No issue is missing from the sprint history. | High | Pending
SPRINT-003 | Verify active sprint validation | • An active sprint exists in the migrated project | • Open the board and locate the active sprint. • Review the sprint's issue list, dates, and progress indicators. • Compare the active sprint's issue list and dates against the source environment. | • The active sprint displays the correct issues and dates consistent with the source environment. | High | Pending
SPRINT-004 | Verify future/planned sprints | • A known future sprint name is available in the source environment | • Open the Backlog view and locate the future sprint. • Review the issues planned/assigned to the future sprint. • Compare the future sprint's planned issue list against the source environment. | • The future sprint and its planned issues are present and match the source environment. | Medium | Pending
SPRINT-005 | Verify burndown and velocity reports where applicable | • Tester has access to the board Reports section with historical sprint data | • Open the board's Reports section. • Open the Burndown Chart for a completed sprint. • Open the Velocity Chart and review historical sprint velocity. • Verify the Burndown Chart renders data consistent with the sprint's known scope/completion. • Verify the Velocity Chart displays historical sprints with plausible completed-vs-committed values. | • Burndown and Velocity reports render without error and reflect data consistent with the source environment's historical sprints. | Low | Pending

## 12 Xray
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
XRAY-001 | Verify Xray is installed and accessible in Jira Cloud | • Tester has an authorized Xray user account on Jira Cloud | • Log in to Jira Cloud as an authorized user. • Navigate to the Xray menu/app section (e.g. via the top navigation or app switcher). • Confirm the Xray license/app status. • Verify Xray appears as an installed and active app. • Verify the authorized user can open Xray screens without a licensing or access error. | • Xray is installed, licensed, and accessible in Jira Cloud without errors. • Authorized users can open Xray functionality successfully. | Critical | Pending
XRAY-002 | Verify migrated Test issue retains steps, data, and expected results | • A known source Test issue key (<SOURCE_ISSUE_KEY>) is available | • Open the migrated Test issue <SOURCE_ISSUE_KEY>. • Open the Test Details/Steps panel and review each step, its test data, and expected result. • Review any associated preconditions and evidence/attachments. • Compare the number of steps and their action/data/expected result content against the source Test. • Compare linked preconditions and evidence against the source Test. | • The migrated Test issue displays the same steps, test data, and expected results as the source Test, in the same order. • Linked preconditions and evidence are present and unchanged. | Critical | Pending
XRAY-003 | Verify migrated Precondition issue type | • A known source Precondition issue key (<SOURCE_ISSUE_KEY>) linked to one or more Tests is available | • Open the migrated Precondition issue <SOURCE_ISSUE_KEY>. • Review the precondition definition/details. • Review the list of associated Test issues. • Compare the precondition content against the source issue. • Compare the list of associated Tests against the source issue. | • The Precondition issue's content and its associated Test issues match the source environment exactly. | High | Pending
XRAY-004 | Verify Xray Test Set migration | • A known source Test Set issue key (<SOURCE_ISSUE_KEY>) is available | • Open the migrated Test Set <SOURCE_ISSUE_KEY>. • Review the list of Tests associated with the Test Set. • Review the Test Set's summary, description, and any custom fields. • Compare the associated Test list (count and identity) against the source Test Set. • Compare Test Set metadata against the source Test Set. | • The Test Set contains the correct, complete list of associated Tests and preserves its metadata, matching the source environment. | High | Pending
XRAY-005 | Verify Xray Test Execution migration | • A known source Test Execution issue key (<SOURCE_ISSUE_KEY>) is available | • Open the migrated Test Execution <SOURCE_ISSUE_KEY>. • Review the list of associated Tests and their individual run status (Pass/Fail/Executing/Todo). • Open one test run's execution details and review recorded evidence/comments. • Review the execution's environment/version fields and execution date/history. • Compare associated Tests and their run status against the source Test Execution. • Compare execution evidence, comments, and environment/version fields against the source. | • The Test Execution shows the correct associated Tests with matching run status, evidence, and metadata consistent with the source environment. • Execution history is preserved. | Critical | Pending
XRAY-006 | Verify Xray Test Plan migration | • A known source Test Plan issue key (<SOURCE_ISSUE_KEY>) is available | • Open the migrated Test Plan <SOURCE_ISSUE_KEY>. • Review the list of linked Test Executions. • Review the list of Tests associated with the Test Plan and their overall status. • Compare linked Test Executions against the source Test Plan. • Compare associated Tests and overall status against the source Test Plan. | • The Test Plan's linked Test Executions and associated Tests match the source environment, including overall test status. | High | Pending
XRAY-007 | Verify end-to-end Xray traceability: Requirement to Test to Test Execution to Defect | • A known Requirement issue (<SOURCE_ISSUE_KEY>) linked to a Test, a Test Execution, and a Defect is available | • Open the Requirement issue and navigate to its linked Test(s) via the Tests panel. • From the Test, navigate to its Test Execution(s). • From the failed test run (if applicable), navigate to the linked Defect issue. • Confirm the Defect links back to the originating Test/Test Execution. • Verify each link in the chain (Requirement -> Test -> Test Execution -> Defect) resolves to the correct migrated Cloud issue. • Verify the traceability report/coverage view (if available) reflects the full chain. | • The full Requirement -> Test -> Test Execution -> Defect chain is navigable and each relationship matches the source environment. • No link in the traceability chain is broken or missing. | Critical | Pending
XRAY-008 | Verify Xray reporting and test coverage functions | • Tester has access to Xray reporting for SFDC Development and/or SFDC Operations | • Open the Xray Test Coverage (or equivalent) report for a Requirement issue or a set of Requirements. • Review coverage percentages and status breakdown. • Open the Traceability Matrix/report (if available) and review the Requirement-to-Test mapping. • Verify coverage figures are consistent with the number and status of migrated Tests/Test Executions. • Verify the traceability report reflects the correct Requirement-to-Test relationships. | • Xray reporting functions render successfully and reflect data consistent with the migrated Tests, Test Executions, and Requirements. | Medium | Pending
XRAY-009 | Verify Xray test evidence and attachments | • A known Test Execution/test run with attached evidence is available | • Open the Test Execution and locate the specific test run containing evidence. • Open the Evidence section and review each attached file. • Download/open each evidence file to confirm it is not corrupted. • Compare the evidence file list and names against the source Test Execution. • Verify each evidence file opens correctly without corruption. | • All evidence/attachments on the migrated Test Execution are present, correctly named, and open without corruption, matching the source environment. | High | Pending

## 13 Integrations
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
INT-001 | Verify configured development tool integration panel is visible on issues | • A known migrated issue with development tool integration data is available | • Open the migrated issue and locate the Development panel/section. • Review the summary counts shown (e.g. commits, branches, pull/merge requests, builds, deployments) as applicable to the configured development tool integration within the migration scope. • Compare the development panel summary information against the source environment where comparable data is available. | • The development tool integration panel is visible on the migrated issue and reflects information consistent with the configured integration in scope. • No integration panel errors are displayed. | Medium | Pending
INT-002 | Verify commit/pull-request links open correctly from Jira issues | • A known migrated issue with at least one commit or pull/merge request link is available | • Open the migrated issue's Development panel. • Select a listed commit or pull/merge request link. • Confirm the destination page loads correctly. • Verify the link opens the correct commit/PR record in the configured development tool integration within the migration scope. | • Commit and pull/merge request links open the correct destination without errors. • No link results in a broken or unauthorized-access page. | Medium | Pending
INT-003 | Verify build and deployment information displays correctly | • A known migrated issue with associated build/deployment information is available | • Open the migrated issue's Development panel. • Review the Builds and Deployments sections (if present). • Confirm build/deployment status indicators render correctly. • Compare the build/deployment status and identifiers against the source environment where comparable data is available. | • Build and deployment information displays correctly on the migrated issue, consistent with the configured integration in scope. | Low | Pending

## 14 Security & Permissions
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
SEC-001 | Verify Administrator role access | • A test account provisioned with the Jira Administrator role is available | • Log in as the Administrator test account. • Navigate to Jira Settings > System/Global settings. • Confirm access to user management, scheme configuration, and app management. • Verify all expected administration areas are accessible without permission errors. | • The Administrator account has full access to Jira Cloud administration areas consistent with its role in the source environment. | Critical | Pending
SEC-002 | Verify Project Administrator role access | • A test account provisioned with the Project Administrator role for one of the in-scope projects is available | • Log in as the Project Administrator test account. • Open Project settings for the assigned project and confirm access to configuration screens. • Attempt to access Jira Settings > System/Global settings. • Verify project-level configuration access is granted. • Verify global administration settings remain restricted (unless the user also holds global admin rights in the source environment). | • The Project Administrator can manage project-level settings for their assigned project and is correctly restricted from unrelated global settings, consistent with the source environment. | High | Pending
SEC-003 | Verify Developer/Tester standard role access | • A test account provisioned with a Developer or Tester role in SFDC Development or SFDC Operations is available | • Log in as the Developer/Tester test account. • Create, edit, and transition an issue in the authorized project. • Open and execute a Test issue in Xray (for Tester role). • Verify all expected day-to-day actions succeed without unexpected permission errors. • Verify the user cannot perform actions restricted to higher-privileged roles (e.g. project configuration changes). | • The Developer/Tester account can perform expected standard actions and is correctly restricted from administrative actions, consistent with the source environment. | High | Pending
SEC-004 | Verify Viewer/read-only user access restrictions | • A test account provisioned with a Viewer/read-only role is available | • Log in as the Viewer test account. • Open an issue and confirm it can be viewed. • Attempt to edit, transition, or delete the issue. • Verify view access succeeds. • Verify edit/transition/delete actions are blocked or the corresponding controls are not available. | • The Viewer account can view issue content but is correctly prevented from editing, transitioning, or deleting issues, consistent with the source environment. | High | Pending
SEC-005 | Verify restricted/issue-security-level user access is enforced | • A test account known to be excluded from a specific Issue Security Level, and an issue using that security level, are available | • Log in as the restricted test account. • Attempt to open the issue protected by the issue security level (via direct URL/issue key search). • Attempt to locate the issue via search/JQL. • Verify the restricted account receives an appropriate access-denied response and cannot view the issue's content. • Verify the issue does not appear in the restricted account's search results. | • The restricted user cannot view or find the issue protected by the issue security level, consistent with the source environment's security configuration. | Critical | Pending

## 15 Confluence Space
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
CONF-001 | Verify SFSUPPORTDE space exists with correct key and name | • Test Environment migration is completed • tester has valid Confluence Cloud access | • Log in to Confluence Cloud. • Navigate to Spaces > View all spaces. • Locate and open the SFSUPPORTDE space. • Compare the space key and space name against the source environment. | • The SFSUPPORTDE space is present with the expected space key and name, and opens successfully. | Critical | Pending
CONF-002 | Verify authorized users can access the SFSUPPORTDE space | • A test account known to have had access to SFSUPPORTDE is available | • Log in as the authorized test account. • Navigate to the SFSUPPORTDE space and open a representative page. • Verify the space and page open without an authorization error. • Compare the access level against the source environment (<SOURCE_USER> access level). | • The authorized user can access the SFSUPPORTDE space and its content without permission errors, consistent with the source environment. | Critical | Pending
CONF-003 | Verify unauthorized users cannot access restricted SFSUPPORTDE content | • A test account known to lack access to SFSUPPORTDE (or a specific restricted page) is available | • Log in as the unauthorized test account. • Attempt to navigate to the SFSUPPORTDE space or the specific restricted page. • Verify access is denied or the space/page is not visible, consistent with the source environment's permission configuration. | • The unauthorized user is correctly prevented from accessing the SFSUPPORTDE space/restricted page, consistent with the source environment. | Critical | Pending

## 16 Confluence Pages
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
CONF-004 | Verify page hierarchy for top-level and nested pages | • A known page hierarchy structure (parent page and nested child pages, <SOURCE_PAGE_NAME>) is available | • Open the SFSUPPORTDE space page tree. • Locate the known parent page <SOURCE_PAGE_NAME> and expand its child pages. • Compare the resulting tree structure against the source environment. • Verify each child page appears under the correct parent, matching the source hierarchy. • Verify no page is missing or nested incorrectly. | • The page hierarchy in Cloud matches the source environment exactly, with all parent/child relationships preserved. | High | Pending
CONF-005 | Verify page content, formatting, and tables render correctly | • A known source page (<SOURCE_PAGE_NAME>) containing formatted text and at least one table is available | • Open the page <SOURCE_PAGE_NAME>. • Review text formatting (headings, bold/italic, lists, code blocks). • Review any embedded tables for correct structure and data. • Compare formatting and table structure/content against the source page. | • The page's content, formatting, and tables render correctly and match the source page's structure and data. | High | Pending
CONF-006 | Verify pages containing images and macros render correctly | • A known source page (<SOURCE_PAGE_NAME>) containing images and macros (e.g. Table of Contents, Status, Info panel) is available | • Open the page <SOURCE_PAGE_NAME>. • Review each embedded image for correct rendering. • Review each macro for correct rendering and functional behavior (e.g. Table of Contents links, Status lozenge color). • Compare image rendering and macro output against the source page. | • Images and macros on the migrated page render correctly and function consistent with the source page. | High | Pending
CONF-007 | Verify page labels and page restrictions are preserved | • A known source page (<SOURCE_PAGE_NAME>) with labels and a restriction is available | • Open the page <SOURCE_PAGE_NAME> and review its labels. • Review the page's restriction settings (Restrictions > view/edit). • Compare the label list against the source page. • Compare the restriction configuration (restricted users/groups) against the source page. | • Page labels and restrictions on the migrated page match the source page exactly. | Medium | Pending
CONF-008 | Verify page version/history is available where supported | • A known source page (<SOURCE_PAGE_NAME>) with multiple historical versions is available | • Open the page <SOURCE_PAGE_NAME>. • Open Page History and review the list of versions. • Open an older version and compare its content to the expected historical content. • Compare the number of versions and their authorship/timestamps against the source page (where version history migration is supported). | • Page version history is available and consistent with the source environment, or is documented as a known migration exception if not supported by the migration approach. | Low | Pending

## 17 Confluence Attachments
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
CONF-009 | Verify Confluence attachments exist with preserved names | • A known source page (<SOURCE_PAGE_NAME>) with attachments (<SOURCE_ATTACHMENT_NAME> list) is available | • Open the page <SOURCE_PAGE_NAME> and open the Attachments list. • Compare the attachment count and filenames against the source page. • Verify each attachment filename matches the source exactly. | • All attachments from the source page are present in Cloud with matching filenames and count. | High | Pending
CONF-010 | Verify Confluence attachments open and download without corruption | • A known source page attachment (<SOURCE_ATTACHMENT_NAME>) is available | • Open the attachment from the page. • Download the file and open it locally. • Compare file size/content against the source file. • Verify the file opens without corruption and matches the expected source file. | • The attachment opens and downloads successfully with content matching the source file, with no corruption. | High | Pending
CONF-011 | Verify embedded documents open correctly | • A known source page containing an embedded document is available | • Open the page containing the embedded document. • View the inline preview (if supported). • Open the document in full view/download it. • Verify the embedded document renders/opens correctly and its content matches the source document. | • The embedded document opens correctly with content matching the source, with no corruption. | Medium | Pending
CONF-012 | Verify embedded images render correctly | • A known source page with inline embedded images is available | • Open the page and review each inline embedded image. • Confirm image resolution, placement, and captions (if used) are preserved. • Compare embedded image rendering against the source page. | • Embedded images render correctly, in the correct placement and resolution, consistent with the source page. | Medium | Pending

## 18 Confluence Links
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
LINK-006 | Verify Confluence page links to Jira issues resolve correctly | • A known source page (<SOURCE_PAGE_NAME>) containing a Jira issue link/macro referencing <SOURCE_ISSUE_KEY> is available | • Open the page <SOURCE_PAGE_NAME>. • Locate the Jira issue link or Jira issue macro. • Click through to the referenced issue. • Verify the link/macro renders the correct issue key, summary, and status. • Verify clicking navigates to the correct migrated Jira Cloud issue, not a broken/legacy URL. | • The Jira issue link/macro on the Confluence page correctly displays and navigates to the corresponding migrated Jira Cloud issue. | High | Pending
LINK-007 | Verify internal Confluence links (parent/child and cross-page) resolve correctly | • A known source page (<SOURCE_PAGE_NAME>) containing links to other SFSUPPORTDE pages is available | • Open the page <SOURCE_PAGE_NAME>. • Click each internal link to another SFSUPPORTDE page. • Use the page tree/breadcrumbs to navigate to the parent page. • Verify each internal link opens the correct destination page. • Verify parent/child breadcrumb navigation is accurate. | • All internal Confluence links and parent/child navigation correctly resolve to the expected migrated pages. | Medium | Pending
LINK-008 | Verify SharePoint links behavior after migration | • A known source page (<SOURCE_PAGE_NAME>) containing a SharePoint link is available | • Open the page <SOURCE_PAGE_NAME>. • Click the SharePoint link. • If the link fails, confirm whether the failure is due to the migration or an intentionally deprecated/expected exception. • Verify the link opens the expected SharePoint destination. • If the destination is intentionally no longer valid, confirm it is documented as an expected migration exception rather than a defect. | • The SharePoint link resolves correctly, or, if it does not, is documented as an expected migration exception rather than logged as an unexplained defect. | Medium | Pending
LINK-009 | Verify external website/document links resolve correctly | • A known source page (<SOURCE_PAGE_NAME>) containing an external link is available | • Open the page <SOURCE_PAGE_NAME>. • Click each external link. • Confirm the destination loads as expected. • Verify the external destination loads correctly and is unaffected by the migration. | • External website/document links continue to resolve correctly after migration, with no unexpected breakage introduced by the migration. | Low | Pending

## 19 Confluence Search
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
SEARCH-005 | Verify Confluence page and keyword search returns migrated content | • A known source page name (<SOURCE_PAGE_NAME>) and a known keyword from its content are available | • Use Confluence Cloud search to search for the exact page title <SOURCE_PAGE_NAME>. • Use Confluence Cloud search to search for a known keyword from the page's content. • Verify the title search returns the expected page as a top result. • Verify the keyword search returns the expected page in the results. | • Both title-based and keyword-based searches return the expected migrated page. | High | Pending
SEARCH-006 | Verify Confluence search by label | • A known label applied to one or more source pages is available | • Use Confluence search filters (or the label browser) to search by the known label. • Review the returned list of pages. • Compare the returned page list against the expected set of labeled pages from the source environment. | • Label-based search returns the complete, correct set of pages consistent with the source environment. | Medium | Pending
SEARCH-007 | Verify Confluence attachment search where supported | • A known attachment filename (<SOURCE_ATTACHMENT_NAME>) is available | • Use Confluence search to search for the attachment filename <SOURCE_ATTACHMENT_NAME>. • Verify the search returns the page containing the attachment (where this search capability is supported by the environment). | • The attachment search returns the expected page containing the attachment, where this capability is supported. | Low | Pending

## 20 Jira-Confluence Cross Valida
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
LINK-010 | Verify Jira issues linking to Confluence pages resolve correctly | • A known migrated Jira issue (<SOURCE_ISSUE_KEY>) linked to a Confluence page (<SOURCE_PAGE_NAME>) is available | • Open the Jira issue <SOURCE_ISSUE_KEY>. • Locate the Confluence page link (in description, comment, or the Confluence pages panel/remote link). • Click through to the Confluence page. • Verify the link opens the correct migrated Confluence Cloud page, not a broken/legacy URL. | • The link from the Jira issue correctly opens the corresponding migrated Confluence Cloud page. | High | Pending
LINK-011 | Verify Confluence macros embedding Jira issues/filters function correctly | • A known source page (<SOURCE_PAGE_NAME>) containing a Jira issue or Jira filter macro is available | • Open the page <SOURCE_PAGE_NAME>. • Review the Jira macro output (single issue details or filter result table). • Confirm the macro is correctly connected to the migrated Jira Cloud instance (not the old On-Premises instance). • Verify the macro output matches the current state of the referenced Jira Cloud issue(s)/filter. | • The Jira macro renders correctly, is connected to the migrated Jira Cloud instance, and reflects accurate, current issue data. | High | Pending
LINK-012 | Verify navigation between Jira Cloud and Confluence Cloud | • Tester has access to both migrated Jira Cloud and Confluence Cloud | • Log in to Jira Cloud. • Use the app switcher (or a cross-link) to navigate to Confluence Cloud. • Navigate back to Jira Cloud using the app switcher. • Verify navigation between the two applications is seamless and does not require re-authentication (if SSO is configured). | • The user can navigate between Jira Cloud and Confluence Cloud without errors or unexpected re-authentication prompts. | Medium | Pending

## 21 Data Reconciliation
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
DATA-006 | Verify total Jira issue count reconciliation overall and by project | • Source issue counts (<SOURCE_COUNT>) overall and per project are available from the Migration Team's pre-migration report | • Run a JQL query for all issues in scope (both projects) and note the total count. • Run separate JQL queries for project = SFDC Development and project = SFDC Operations and note each count. • Compare the Cloud value <TARGET_COUNT> against the corresponding source value <SOURCE_COUNT> for the overall total and for each project. | • The total migrated issue count and per-project counts match the corresponding source counts exactly, or any variance is documented and explained. | Critical | Pending
DATA-007 | Verify issue counts by issue type reconciliation | • Source issue counts by issue type (<SOURCE_COUNT>) are available from the Migration Team's pre-migration report | • Run a JQL query filtered by issuetype for each of the 13 in-scope issue types and note each count. • Compare each issue type's Cloud count <TARGET_COUNT> against the corresponding source count <SOURCE_COUNT>. | • Issue counts for all 13 issue types match the source environment exactly, or any variance is documented and explained. | Critical | Pending
DATA-008 | Verify issue counts by status, priority, version, and component | • Source issue counts by status/priority/version/component (<SOURCE_COUNT>) are available | • Run JQL queries filtered by each key status, priority, version, and component and note the counts. • Compare each Cloud count <TARGET_COUNT> against the corresponding source count <SOURCE_COUNT>. | • Issue counts by status, priority, version, and component match the source environment exactly, or any variance is documented and explained. | High | Pending
DATA-009 | Verify Xray artifact count reconciliation | • Source Xray artifact counts (<SOURCE_COUNT>) are available from the Migration Team's pre-migration report | • Run JQL queries filtered by issuetype = Test, Test Set, Test Execution, and Test Plan and note each count. • Compare each Cloud count <TARGET_COUNT> against the corresponding source count <SOURCE_COUNT>. | • Xray artifact counts (Tests, Test Sets, Test Executions, Test Plans) match the source environment exactly, or any variance is documented and explained. | Critical | Pending
DATA-010 | Verify Confluence page count reconciliation | • Source page count (<SOURCE_COUNT>) for SFSUPPORTDE is available from the Migration Team's pre-migration report | • Open SFSUPPORTDE space details/analytics (or export the page tree) and note the total page count. • Compare the Cloud page count <TARGET_COUNT> against the source count <SOURCE_COUNT>. | • The total migrated page count for SFSUPPORTDE matches the source environment exactly, or any variance is documented and explained. | Critical | Pending
DATA-011 | Verify attachment count reconciliation for Jira and Confluence | • Source attachment counts (<SOURCE_COUNT>) for Jira and Confluence are available from the Migration Team's pre-migration report | • Use available reporting/export capability to obtain the total attachment count for SFDC Development and SFDC Operations. • Use available reporting/export capability to obtain the total attachment count for SFSUPPORTDE. • Compare each Cloud attachment count <TARGET_COUNT> against the corresponding source count <SOURCE_COUNT>. | • Attachment counts for Jira and Confluence match the source environment exactly, or any variance is documented and explained. | High | Pending

## 22 Migration Exceptions
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
EXC-001 | Identify missing or duplicate Jira issues | • Reconciliation counts from DATA-006/DATA-007 and a sample list of source issue keys are available | • Cross-check the reconciliation counts from DATA-006 and DATA-007 for discrepancies. • Spot-check a sample of source issue keys (<SOURCE_ISSUE_KEY>) to confirm each exists exactly once in Cloud. • Log any missing issue as a migration defect with the source issue key. • Log any duplicate issue as a migration defect with both Cloud issue keys involved. | • No missing or duplicate issues are found; any discrepancy identified is logged as a migration defect with supporting evidence (issue keys, counts). | Critical | Pending
EXC-002 | Identify broken links and missing attachments | • Results from LINK-001 to LINK-012 and ATT-001 to ATT-005 / CONF-009 to CONF-012 test executions are available | • Review results from all link and attachment test cases executed so far. • Classify each failure as either a genuine migration defect or an expected/documented exception (e.g. intentionally deprecated On-Premises URL). • Log each unresolved broken link or missing attachment as a migration defect with reproduction details. | • All broken links and missing attachments identified during testing are either resolved, or classified and logged as migration defects/expected exceptions. | High | Pending
EXC-003 | Identify incorrect user mapping or permission discrepancies | • Results from ENV-004, SEC-001 to SEC-005, CONF-002, and CONF-003 test executions are available | • Review results from environment, security, and Confluence permission test cases. • Cross-check a sample of <SOURCE_USER> to <CLOUD_USER> mappings against the Migration Team's user mapping document. • Log any user missing from Cloud, mapped to the wrong account, or granted incorrect permissions as a migration defect. | • No unresolved user mapping or permission discrepancies remain; any issue found is logged as a migration defect with the affected user and expected vs. actual access. | Critical | Pending
EXC-004 | Identify missing history, incorrect custom-field values, or workflow/status mapping issues | • Results from DATA-001 to DATA-005 and CFG-001 to CFG-006 test executions are available | • Review results from data integrity and configuration test cases. • Confirm each identified discrepancy has been reproduced and documented with the affected issue key/field. • Log each confirmed discrepancy (missing history, incorrect custom field value, incorrect workflow/status mapping) as a migration defect. | • No unresolved history, custom-field, or workflow mapping discrepancies remain; any issue found is logged as a migration defect with reproduction evidence. | High | Pending
EXC-005 | Identify missing Xray data or Confluence page/hierarchy issues | • Results from XRAY-001 to XRAY-009, DATA-009, CONF-001 to CONF-008, and DATA-010 test executions are available | • Review results from Xray and Confluence test cases and reconciliation counts. • Confirm each identified discrepancy has been reproduced and documented. • Log each confirmed missing Xray artifact or Confluence page/hierarchy defect with supporting evidence (issue key/page name, expected vs. actual). | • No unresolved missing Xray data or Confluence page/hierarchy issues remain; any issue found is logged as a migration defect with supporting evidence. | Critical | Pending

## 23 Handover Readiness
TestID | Test Name | Pre-Requisite | Test Detail | Expected Outcome | Reference & Status | Status
HAND-001 | Verify critical Jira functions checklist for handover | • All Critical-priority Jira-related test cases in this suite have been executed | • Compile the execution results for all Critical-priority test cases with prefixes ENV, JIRA, DEV, OPS, CFG, DATA, LINK, SEARCH, and BOARD. • Confirm each has a Pass result or a documented, accepted exception. • Verify no Critical-priority Jira test case has a Fail status without a documented resolution or accepted risk. | • All Critical-priority Jira test cases are passed or have a documented, accepted exception, supporting readiness for handover. | Critical | Pending
HAND-002 | Verify critical Xray functions checklist for handover | • All Critical-priority Xray-related test cases in this suite have been executed | • Compile the execution results for all Critical-priority test cases with prefix XRAY, plus DATA-009. • Confirm each has a Pass result or a documented, accepted exception. • Verify no Critical-priority Xray test case has a Fail status without a documented resolution or accepted risk. | • All Critical-priority Xray test cases are passed or have a documented, accepted exception, confirming Xray is usable and traceable for handover. | Critical | Pending
HAND-003 | Verify critical Confluence functions checklist for handover | • All Critical-priority Confluence-related test cases in this suite have been executed | • Compile the execution results for all Critical-priority test cases with prefix CONF, plus DATA-010. • Confirm each has a Pass result or a documented, accepted exception. • Verify no Critical-priority Confluence test case has a Fail status without a documented resolution or accepted risk. | • All Critical-priority Confluence test cases are passed or have a documented, accepted exception, supporting readiness for handover. | Critical | Pending
HAND-004 | Verify user access and permissions sign-off checklist | • All relevant environment, security, and permission test cases have been executed | • Compile the execution results for ENV-003, ENV-004, SEC-001 to SEC-005, CONF-002, CONF-003, and EXC-003. • Confirm each has a Pass result or a documented, accepted exception. • Verify no unresolved permission or access discrepancy remains open. | • User access and permission validation is complete, with all Critical/High findings resolved or formally accepted, supporting handover sign-off. | Critical | Pending
HAND-005 | Verify no unresolved Severity 1/Critical migration defects or data-loss issues remain | • The consolidated migration defect log and results of EXC-001 to EXC-005 are available | • Review the migration defect log for any open Severity 1/Critical entries. • Cross-check against the findings from EXC-001 to EXC-005 for unresolved data-loss issues. • Verify all Severity 1/Critical defects are either resolved and re-verified, or explicitly accepted by the Application/Project Team with sign-off. | • No open Severity 1/Critical migration defects or unresolved data-loss issues remain; any exceptions are explicitly accepted and documented. | Critical | Pending
HAND-006 | Verify Migration Team sign-off readiness and documented exceptions | • All test cases in this suite have been executed and results/evidence recorded | • Compile a summary of overall pass/fail results across all test categories in this suite. • Compile the list of documented/accepted migration exceptions. • Obtain formal Migration Team sign-off confirming handover readiness. • Verify the summary report is complete, all exceptions are documented with business/technical justification, and sign-off has been recorded. | • A complete summary report and documented exception list are available, and the Migration Team has formally signed off on handover readiness to the Application/Project Team. | Critical | Pending